Subject │ Minutes of the Seventh Management Committee Meeting of COST Action CA16216: “Network on the Coordination and Harmonisation of European Occupational Cohorts (OMEGA-NET)” Online Meeting, 7 April 2022 # 1) Welcome to participants The participants were welcomed by Ingrid Sivesind Mehlum (ISM), Chair, and by Michelle Turner (MCT), Vice-Chair of the Action. # 2) VERIFICATION OF THE PRESENCE OF TWO-THIRDS OF tHE PARTICIPATING COST COUNTRIES CSO Approval:; 23/06/2017. Start of the Action:; 26/10/2017. End of Action:; 25/04/2022. MoU reference:; COST 027/17. Number of COST Countries having accepted the MoU:; 32. Number of COST Countries intending to accept the MoU:; 0. Number of parties present at the meeting:; 22. The quorum (2/3 of COST Countries participating in the Action) was reached: 22 COST countries out of 32 attended the meeting (COST doc. 134/14 “COST Action Management Monitoring and Final Assessment” Annex I, Article 8). A listing of the participants at the meeting is provided in Annex 1. 3) ADOPTION OF AGENDA The agenda (Annex 2) for the 7th Management Committee (MC) meeting was adopted. 4) APPROVAL OF MINUTES AND MATTERS ARISING OF LAST MEETING The minutes of the last meeting were approved and a summary of the matters arising of the last meeting was provided (see Annex 3 and 4 – presentation for a summary of the matters). 5) UPDATE FROM THE ACTION CHAIR a) Status of Action: start and end dates of Action, participating COST countries, participating NNC/ IPC institutions and Specific Organisations - An overview of the status of the Action was provided by the Action Chair (see Annex 4). It was noted that 50% of participating COST countries are ITCs. b) Short Term Scientific Missions (STSM) and ITC Conference Grants: review of completed reports and new applications (ISM) - A summary of STSMs and ITC conference grants was provided (see Annex 4) - A total of 25 STSMs have been completed in the Action to date overall, including 2 in Grant Period 4 and 3 in Grant Period 5, the geographic distribution of home and host institutions were described - There was 1 ITC conference grant in Grant Period 4 and 0 in Grant Period 5 - A total of 3 Virtual Mobility Grants were completed in Grant Period 4 and 1 is planned in Grant Period 5 6) IMPLEMENTATION OF COST POLICIES ON a) Promotion of gender balance and Early Career Investigators (ECIs) - An overview was provided (see Annex 4) - Gender balance: 57 MC Members: 36 women (63%), 241 Action contacts: 153 women (63%), note 67 had information on gender missing - Early Career Investigators (ECI): we have held 3 young researcher sessions at previous meetings, one webinar of young researchers, and engagement through grants (STSM, VMG, ITC conference grants) b) Inclusiveness and Excellence (see below list of Inclusiveness Target Countries) - An overview of the promotion of inclusiveness and excellence was provided (see Annex 4) - 32 countries: 16 Inclusiveness Target Countries (ITC) (50%) - 58 MC Members: 27 ITC (47%) - 200 Action contacts from COST countries: 89 ITC (45%) - 7) MONITORING OF THE ACTION - A draft version of the Final Report was circulated to the MC before the meeting - Written feedback from several MC members has been received - Projects mentioned by the Polish MC member in Day 1 will be included in the Final Report - The Action chair will circulate the next version of the draft Final Report and ask if any content is missing, including related to new projects or publications # 8) update from the grant holder: action budget status The grant holder (Michelle Turner) provided an update of the budget status. A total budget of 77,360.50 EUR was allocated for this fifth grant period (1/11/2021 to 25/04/2022). - The Action has spent so far a total of 55,181.32 EUR in this final grant period - Additional invoices and travel claims are expected to be received over the next few weeks by the Grant Holder - The MC was encouraged to let us know as soon as possible if any new requests for funds for publication charges for Action-related publications - A new VMG application was received, a vote was held to ask the MC if they “approve that 1500 EUR of the budget is re-allocated from other activities to a Virtual Mobility Grant (VMG)?” which was approved (only 1 MC member disagreed) 9) Follow-up of MoU objectives: progress report of working groups (WG Leaders) See Annex 4, as well as presentations from Day 1 of the meeting. All WGs have achieved excellent progress. Type; Objective. Challenge; Create a network to optimise the use of occupational, industrial, and population cohorts in Europe.. Research Coordination 1; Coordinate and integrate cohorts on occupational health in Europe.. Research Coordination 2; Implement an online interactive tool with detailed information on existing cohorts.. Research Coordination 3; Facilitate work on harmonisation of occupational exposure and standardisation of health outcome information and new protocols for data collection.. Research Coordination 4; Promote stakeholder engagement from the start of the project.. Capacity Building 1; Connect scientific communities on occupational health in Europe.. Capacity Building 2; Provide networking and leadership opportunities for Early Career Investigators, as well as researchers from COST Inclusiveness Target Countries.. Capacity Building 3; Provide training in occupational epidemiology and exposure assessment..

10) Scientific planning a) Scientific strategy (MoU objectives, GP Goals, WG tasks and deliverables) The following deliverables are contained in Grant Period 5: - D2.3. Position papers for harmonisation of exposure and health outcome data have been completed, and a listing is presented on the Action website. - D2.5. Final data management plan, including a comparison of future approaches for decentralised data, has been sent to the Action Chair - D2.6. Final report on ethical framework and procedures has been sent to the Action Chair - D3.1 Position papers on the collection of specific exposure and outcome data on specific topics have been completed, and a listing is presented on the Action website. - D4.5. Communication materials: Newsletters for stakeholders. A final newsletter is under preparation and will be completed before the end of the Action. - D4.6. OMEGA-NET training materials. The in-person training course was held 28 March – April 1, 2022, in Barcelona, Spain, the training materials will be placed on the Action website. - D4.7 The stakeholder workshop is planned as part of the final meeting, to take place following the MC meeting. b) Workflow and approval of deliverables by WG leadership - The MC was reminded that deliverables and other products resulting from the WGs are to be sent to the Core Group for approval before being submitted / published both 1) For information and 2) If asking for funding c) Dissemination planning (Publications, outreach activities and stakeholder engagement) - A list of outputs includes: - Publications: 21 published, 1 accepted, others in review, submitted or in progress - Twitter: 120 Tweets - Newsletters: 4 (+1 planned) - ITC Conference grants: 8 - Short-term scientific missions (STSM): 25 - Virtual Mobility Grants: 3 (+1 planned) - Training courses: 4 - Webinars: 7 - It was also noted that 3 videos have been produced d) Long-term sustainability of the Action - The Action was extended until April 25, 2022, including budget from COST, due to COVID-19 - We are working on possibilities for continued networking and collaboration including with funding (COST grants, research calls) or without funding 11) Requests to join the Action from: - For any new requests received since the last MC meeting, the persons were informed that most work is already completed. 12) update from the cost association, if a representative is present - Guiseppe Lugano and Katchamon Nimprang were present and noted: - Congratulations to OMEGA-NET for its achievements - The structure and content of Day 1 was of high quality both in terms of research and of capacity building. In particular, the discussion on excellence and inclusiveness was also appreciated. - COVID-19 has been challenging for COST Actions and has likely had a negative impact on our work, as well as on our ability to spend funds, it was noted that we have been able to successfully use the VMG funding option available - COST is happy to receive any feedback on recent changes in the COST rules - There is a high degree of competition for COST Actions, and it will be important to start to plan on how to continue our work even without funding (this will be discussed in the next plenary session), COST would like to be kept informed about our progress if we are able to continue either in the scenario of additional funding or no new additional funding - Some specific ideas for continued collaboration include: social media groups, an annual meeting, working on special issues of a journal - There are likely other longer term impacts of the Action that will be observed later in the future, COST would like to be kept updated about longer term developments - COST will invite the chair to prepare a short article for the COST website highlighting key achievements, stories, new events - COST will invite newly ended Actions to participate in some COST activities in the future 13) AOB - None 14) Summary of MC decisions A summary of MC decisions was provided by the Vice Chair: - The MC has approved the minutes of the last meeting - The MC has approved that 1,500 EUR of the budget is re-allocated from other activities to a Virtual Mobility Grant (VMG) (only 1 MC member disagreed) - Thanks for the support of the COST Association and its vision for research in Europe. Funding from COST was essential to achieving the goals of OMEGA-NET 15) Closing The meeting closed, congratulations regarding the achievements of the Action were provided by MC members and observers.

## Annex 1 – MC meeting REGISTRATIONS

## Annex 2 – Agenda

C)	 ANNEX 3 – MINUTES OF FIFTH MC MEETING

https://omeganetcohorts.eu/events/meeting-omeganet-october-2021-2/

D) ANNEX 4 - PRESENTATION BY ACTION CHAIR (AND VICE CHAIR)